## Issue Tracker
First Assignment VHDL Project by Group 4 OPEN vs. CLOSED ISSUE TRACKER |  |  |  |  | TYPE | PRIORITY | DATE | LAST (days)
[5 empty] | * | * | 2016-03-01 | 30
# | ISSUE | TYPE | PRIORITY | OPENED ON | OPENED BY | CLOSED ON | CLOSED BY | NOTES
1 | PhysDesignRules:372 - Gated clock. | Gated Clock Warning | High | 2016-02-05 | Manuel | 2016-02-11 | Brian Liu | RESOLVED : Clock net MODUL_SET<4> is sourced by a combinatorial pin. This is not good design practice. Use the CE pin to control the loading of data into the flip-flop. The eternal gate clock problem. The system clock must be applied to all registers inside your design, to keep it synchronous. Remember: "Avoid asynchronous design; practice synchronous design until a better methodology comes along". Otherwise you will receive the famous Gated clock warning. Take a look at the Discussion forum post about this subject. After, review the way the up/down counter was implemented in the first course week. Again, check the Discussion forum to look at the up/down counter VHDL files. Notice that to reduce the frequency of the up/down counter we generate a clock enable pulse to be applied to the register. We don't create a slow clock signal using counters to apply it to the clock register input. We create a signal - clock enable (CE) - that inhibits the application of the clock signal to the register, except for one period each x"FFFFF" cycles (or each 16777215 pulses, around 168ms interval).
2 | Xst:1896 - Due to other FF/Latch trimming | Trimming Warning | Low | 2016-02-05 | Manuel | 2016-02-12 | Brian Liu | RESOLVED: A lot of warnings state that: Xst:1896 - Due to other FF/Latch trimming, FF/Latch <timer_md/hours_7> has a constant value of 0 in block <smtWatch>. This FF/Latch will be trimmed during the optimization process. It seems that you declared signals that you are not effectively being use or whose values never change. There are also warnings about incomplete case statements that end up generating latches. This can be easily avoided if you end up your incomplete case statements with when others => sequential statements;
3 | Xst:737 - Found 1-bit latch for signal <blink_flag<7>>. | Latch Waring | Medium | 2016-02-05 | Manuel | 2016-02-12 | Brian Liu | RESOLVED: Xst:737 - Found 1-bit latch for signal <blink_flag<7>>. Latches may be generated from incomplete case or if statements. We do not recommend the use of latches in FPGA/CPLD designs, as they may lead to timing problems.
4 | Incompatibility between the alarm and the clock | Behaviour | Low | 2016-02-05 | Manuel | 2016-02-11 | Brian Liu | RESOLVED: clock goes from 01:00 to 24:59 (normally they go between 00:00 and 23:59), but alarm can be set between 00:00 and 00:59. If you select 00:01 for example, the alarm never goes on. In the same way, the alarm cannot be set between 24:00 and 24:59. You should correct the clock to run between 00:00 and 23:59.
5 | Days of the week seemed not to be working. | Algorithm | High | 2016-02-05 | Manuel |  | Zhili Shao | ON_GOING: In calendar mode, days of the week seemed not to be working. It always displayed an intriguing da:02 no matter if I increment the calendar day or not. Then I understood that I must set it myself :-) Well, what I was expecting is that it determined the day of the week based on the date! Take a look at http://www.wikihow.com/Calculate-the-Day-of-the-Week. It also accepts things like February 31st, 1968, for example. Well, I was expecting an automatic calendar!
6 | Unable to reset Stopwatch | Behaviour | Low | 2016-02-05 | Manuel | 2016-02-10 | Brian Liu | RESOLVED: Now it can be reset by first press Button 2 from timing state to enter pause state (the led will blink) then press Button 3, it will be reset to Zero.
7 | no need to set 23 hours has the maximum for the hour | Behaviour | Low | 2016-02-05 | Manuel | 2016-02-09 | Brian Liu | RESOLVED: It should be possible to set, for example 99 hours and 59 minutes as the maximum time and decrease it until reach zero.
8

## calculations (hidden)
*** This sheet should remain hidden ***
|  |  | Min | 2012-01-01
Max
|  |  | Days | 30
|  |  | Date | 2016-03-01 | 1
|  |  | Type | *
|  |  | Priority | *
[5 empty] | #VALUE! | #VALUE!
[5 empty] | 6 | 4 | Sorted | Sorted
|  | Date | Opened | Closed | Types | Priorities | Types | Priorities
[5 empty] | * | *
| 1 | 2016-02-01 | 0 | 0 | Gated Clock Warning | High | * | *
| 2 | 2016-02-02 | 0 | 0 | Trimming Warning | Low | * | *
| 3 | 2016-02-03 | 0 | 0 | Latch Waring | Medium | Algorithm | High
| 4 | 2016-02-04 | 0 | 0 | Behaviour | 0 | Behaviour | Low
| 5 | 2016-02-05 | 7 | 0 | Algorithm | #N/A | Gated Clock Warning | Medium
| 6 | 2016-02-06 | 7 | 0 | 0 | #N/A | Latch Waring | #NUM!
| 7 | 2016-02-07 | 7 | 0 | #N/A | #N/A | Trimming Warning | #NUM!
| 8 | 2016-02-08 | 7 | 0 | #N/A | #N/A | #NUM! | #NUM!
| 9 | 2016-02-09 | 7 | 1 | #N/A | #N/A | #NUM! | #NUM!
| 10 | 2016-02-10 | 7 | 2 | #N/A | #N/A | #NUM! | #NUM!
| 11 | 2016-02-11 | 7 | 4 | #N/A | #N/A | #NUM! | #NUM!
| 12 | 2016-02-12 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 13 | 2016-02-13 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 14 | 2016-02-14 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 15 | 2016-02-15 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 16 | 2016-02-16 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 17 | 2016-02-17 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 18 | 2016-02-18 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 19 | 2016-02-19 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 20 | 2016-02-20 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 21 | 2016-02-21 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 22 | 2016-02-22 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 23 | 2016-02-23 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 24 | 2016-02-24 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 25 | 2016-02-25 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 26 | 2016-02-26 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 27 | 2016-02-27 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 28 | 2016-02-28 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 29 | 2016-02-29 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 30 | 2016-03-01 | 7 | 6 | #N/A | #N/A | #NUM! | #NUM!
| 31 | 2016-03-02 | 7 | 6
| 32 | 2016-03-03 | 7 | 6
| 33 | 2016-03-04 | 7 | 6
| 34 | 2016-03-05 | 7 | 6
| 35 | 2016-03-06 | 7 | 6
| 36 | 2016-03-07 | 7 | 6
| 37 | 2016-03-08 | 7 | 6
| 38 | 2016-03-09 | 7 | 6
| 39 | 2016-03-10 | 7 | 6
| 40 | 2016-03-11 | 7 | 6
| 41 | 2016-03-12 | 7 | 6
| 42 | 2016-03-13 | 7 | 6
| 43 | 2016-03-14 | 7 | 6
| 44 | 2016-03-15 | 7 | 6
| 45 | 2016-03-16 | 7 | 6
| 46 | 2016-03-17 | 7 | 6
| 47 | 2016-03-18 | 7 | 6
| 48 | 2016-03-19 | 7 | 6
| 49 | 2016-03-20 | 7 | 6
| 50 | 2016-03-21 | 7 | 6
| 51 | 2016-03-22 | 7 | 6
| 52 | 2016-03-23 | 7 | 6
| 53 | 2016-03-24 | 7 | 6
| 54 | 2016-03-25 | 7 | 6
| 55 | 2016-03-26 | 7 | 6
| 56 | 2016-03-27 | 7 | 6
| 57 | 2016-03-28 | 7 | 6
| 58 | 2016-03-29 | 7 | 6
| 59 | 2016-03-30 | 7 | 6
| 60 | 2016-03-31 | 7 | 6
| 61 | 2016-04-01 | 7 | 6
| 62 | 2016-04-02 | 7 | 6
| 63 | 2016-04-03 | 7 | 6
| 64 | 2016-04-04 | 7 | 6
| 65 | 2016-04-05 | 7 | 6